Track 2: Outcomes and Timeline Example

| **Measurable Project Outcomes** | **Project Activities (what specific steps will be taken to meet the outcome)** | **Anticipated Completion Date (MM/YYYY)** |
| --- | --- | --- |
| 1. **Complete new irrigation system for ½ acre community garden**
 | Develop irrigation plan | February 2025  |
|   | Purchase Irrigation Supplies | March 2025 |
|  | Install irrigation system with volunteers | May 2025 |
|  | Project complete | May 2025 |
| 1. **Install hoop house for longer planting season**
 | Solicit quotes for hoop house structure | April 2025 |
|  | Purchase hoop house  | May 2025 |
|  | Install hoop house with volunteers | July 2025 |
|  | Project Complete | September 2025 |
| 1. **Engage Community Members with hands-on build days**
 | Promote irrigation installation day event through social media and flyers, connect with community partners to advertise | April 2025 |
|  | Promote hoop house installation day event through social media and flyers, connect with community partners to advertise | June 2025 |